## Sheet1
Task | Start Date | Days to Complete
Learning distributed computing frameworks | 2019-01-01 | 15
Understanding project requirements | 2019-01-16 | 10
Defining the architecture | 2019-01-27 | 10
Data Extractor | 2019-02-06 | 20
Data Transformer | 2019-02-27 | 20
Data Loader | 2019-03-09 | 20
Implemetation of ui and api | 2019-03-29 | 7
Testing | 2019-04-06 | 10
Final Integration to ThreatModeler | 2019-04-16 | 14
43466